## Sheet1
| Project Leader: Nam le |  |  | Project: Understanding and using Github, Translate Chapter 6 in PMBook v5
| Project Objectives: Get high mark for the 30% of the course "Project management" |  |  | Date: September 7th 2016
OJECTTIVES |  | MAJOR TASKS |  | CHECKLIST | [7 empty] | OWENT/PRIORIT
⃝ | ⃝ | 1 | Plant project (Time, Resource, Budget, Bonus,…), make the happy air for the team | ⃝ | [7 empty] | A
⃝ | ⃝ | 2 | Identyfy requirement (Github and Chapter 6 & PMBook v5) |  | ⃝ | [6 empty] | B | A
⃝ |  | 3 | Introduction about Github |  | ⃝ | [8 empty] | A
⃝ |  | 4 | System requirement to set up Github |  |  | ⃝ | [8 empty] | A
⃝ |  | 5 | Working process (Commit, Pull, Check-out,…) |  |  |  | ⃝ | [7 empty] | B | A
⃝ |  | 6 | Work with Branch (Create, Merge to master,…) |  |  |  | ⃝ | [5 empty] | A | B | C
⃝ |  | 7 | Resolve conflict when chick-in check-out |  |  |  |  | ⃝ | [5 empty] | C | B | A
| ⃝ | 8 | Find the PMBook v5 with licensed |  |  |  |  | ⃝ |  |  |  | A | B
| ⃝ | 9 | To understand what's the book |  |  |  |  | ⃝ | ⃝ |  |  | E | D | C | B | A
| ⃝ | 10 | Translate Chapter 6 to Vietnamese |  |  |  |  | ⃝ | ⃝ |  |  |  | A | B | C | D
⃝ | ⃝ | 11 | Write report | [6 empty] | ⃝ |  | A | B
12
Ricks, Qualitattives, Orther metrics
| ⃝ | A | Misunderstand English document
⃝ | ⃝ | B | Leave in sick
⃝ | ⃝ | C | Time management
⃝ |  | D | Reslove Not equal in knowledge between each members
⃝ | ⃝ | E | Support member | [8 empty] | A | B | C | D | E
F
understand Github | PMBook v5 |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Nam Le | Son Doan | Duc Tran | Thao Pham | Nhut Huynh
Millions
[17 empty] | Labels | Budgeted | Expended
[17 empty] | Other | 5 | 0
[17 empty] | Expenses | 6 | 0
[17 empty] | Capital | 7 | 0
Major Tasks
Summary & Forecast
Objectives
Target Dates
Costs

## WBS dictionary
Project Name: |  |  |  | Project Name:
Work Package ID: | 1 |  |  | Work Package ID: | 2
Work Package Name: | Translate Google |  |  | Work Package Name: | Tìm hiểu SVN
Work Package Description: | Dịch chương 6 bằng google translate, chia ra thành 7 file txt upload len host |  |  | Work Package Description:
Assigned To: | Nam Le, Son Doan | Group/Dept: | 15HTH02 | Assigned To: | Nam Le | Group/Dept: | 15HTH02
Date Assigned: | 2016-09-20 | Date Due: | 2016-09-25 | Date Assigned: | 2016-09-20 | Date Due: | 2016-09-25
Estimated Cost: | N/a | Account Code: |  | Estimated Cost: | N/a | Account Code:
Acceptance Criteria: | 7 file txt từng mục | Resources Assigned: | PMBOK2012-5rd Edition | Acceptance Criteria: | Cài đặt thành công SVN | Resources Assigned:
Deliverables: |  | Assumptions: |  | Deliverables: |  | Assumptions:
Project Name: |  |  |  | Project Name:
Work Package ID: | 1.1 |  |  | Work Package ID: | 2.1
Work Package Name: | Read and edit |  |  | Work Package Name:
Work Package Description: | Đọc từng chương, viết lại theo từng mục |  |  | Work Package Description:
Assigned To: | Son Doan, Duc Tran, Thao Pham, Nhut Huynh | Group/Dept: | 15HTH02 | Assigned To: |  | Group/Dept: | 15HTH02
Date Assigned: | 2016-09-20 | Date Due: | 2016-09-30 | Date Assigned: |  | Date Due:
Estimated Cost: | N/a | Account Code: |  | Estimated Cost: | N/a | Account Code:
Acceptance Criteria: | Có chỉnh sửa file text | Resources Assigned: | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7 | Acceptance Criteria: |  | Resources Assigned:
Deliverables: |  | Assumptions: |  | Deliverables: |  | Assumptions:
Project Name: |  |  |  | Project Name:
Work Package ID: | 1.2 |  |  | Work Package ID: | 2.2
Work Package Name: | Complete |  |  | Work Package Name:
Work Package Description: | Đọc từng chương đã được sửa lại, ghép và hoàn thành file .docx |  |  | Work Package Description:
Assigned To: | Nam le | Group/Dept: | 15HTH02 | Assigned To: |  | Group/Dept: | 15HTH02
Date Assigned: | 2016-09-30 | Date Due: | 2016-05-10 | Date Assigned: |  | Date Due:
Estimated Cost: | N/a | Account Code: |  | Estimated Cost: | N/a | Account Code:
Acceptance Criteria: | 1 file .docx hoàn chỉnh | Resources Assigned: | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7 | Acceptance Criteria: |  | Resources Assigned:
Deliverables: |  | Assumptions: |  | Deliverables: |  | Assumptions:
Project Name:
|  |  |  | Work Package ID: | 2.3
Work Package Name:
Work Package Description:
|  |  |  | Assigned To: |  | Group/Dept: | 15HTH02
|  |  |  | Date Assigned: |  | Date Due:
|  |  |  | Estimated Cost: | N/a | Account Code:
|  |  |  | Acceptance Criteria: |  | Resources Assigned:
|  |  |  | Deliverables: |  | Assumptions:
Project Name:
|  |  |  | Work Package ID: | 2.4
Work Package Name:
Work Package Description:
|  |  |  | Assigned To: |  | Group/Dept: | 15HTH02
|  |  |  | Date Assigned: |  | Date Due:
|  |  |  | Estimated Cost: | N/a | Account Code:
|  |  |  | Acceptance Criteria: |  | Resources Assigned:
|  |  |  | Deliverables: |  | Assumptions: