## Sheet1
| Project Leader: Nam le |  |  | Project: Understanding and using Github, Translate Chapter 6 in PMBook v5
| Project Objectives: Get high mark for the 30% of the course "Project management" |  |  | Date: September 7th 2016
OJECTTIVES |  | MAJOR TASKS |  | CHECKLIST | [7 empty] | OWENT/PRIORIT
⃝ | ⃝ | 1 | Plant project (Time, Resource, Budget, Bonus,…), make the happy air for the team | ⃝ | [7 empty] | A
⃝ | ⃝ | 2 | Identyfy requirement (Github and Chapter 6 & PMBook v5) |  | ⃝ | [6 empty] | B | A
⃝ |  | 3 | Introduction about Github |  | ⃝ | [8 empty] | A
⃝ |  | 4 | System requirement to set up Github |  |  | ⃝ | [8 empty] | A
⃝ |  | 5 | Working process (Commit, Pull, Check-out,…) |  |  |  | ⃝ | [7 empty] | B | A
⃝ |  | 6 | Work with Branch (Create, Merge to master,…) |  |  |  | ⃝ | [5 empty] | A | B | C
⃝ |  | 7 | Resolve conflict when chick-in check-out |  |  |  |  | ⃝ | [5 empty] | C | B | A
| ⃝ | 8 | Find the PMBook v5 with licensed |  |  |  |  | ⃝ |  |  |  | A | B
| ⃝ | 9 | To understand what's the book |  |  |  |  | ⃝ | ⃝ |  |  | E | D | C | B | A
| ⃝ | 10 | Translate Chapter 6 to Vietnamese |  |  |  |  | ⃝ | ⃝ |  |  |  | A | B | C | D
⃝ | ⃝ | 11 | Write report | [6 empty] | ⃝ |  | A | B
12
Ricks, Qualitattives, Orther metrics
| ⃝ | A | Misunderstand English document
⃝ | ⃝ | B | Leave in sick
⃝ | ⃝ | C | Time management
⃝ |  | D | Reslove Not equal in knowledge between each members
⃝ | ⃝ | E | Support member | [8 empty] | A | B | C | D | E
F
understand Github | PMBook v5 |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Nam Le | Son Doan | Duc Tran | Thao Pham | Nhut Huynh
Millions
[17 empty] | Labels | Budgeted | Expended
[17 empty] | Other | 5 | 0
[17 empty] | Expenses | 6 | 0
[17 empty] | Capital | 7 | 0
Major Tasks
Summary & Forecast
Objectives
Target Dates
Costs

## WBS dictionary
Project Name: |  |  |  | Project Name:
Work Package ID: | 1 |  |  | Work Package ID: | 2
Work Package Name: | Translate Google |  |  | Work Package Name: | Tìm hiểu SVN
Work Package Description: | Dịch chương 6 bằng google translate, chia ra thành 7 file txt upload len host |  |  | Work Package Description:
Assigned To: | Nam Le, Son Doan | Group/Dept: | 15HTH02 | Assigned To: | Nam Le | Group/Dept: | 15HTH02
Date Assigned: | 2016-09-20 | Date Due: | 2016-09-25 | Date Assigned: | 2016-09-20 | Date Due: | 2016-09-25
Estimated Cost: | N/a | Account Code: |  | Estimated Cost: | N/a | Account Code:
Acceptance Criteria: | 7 file txt từng mục | Resources Assigned: | PMBOK2012-5rd Edition | Acceptance Criteria: | Cài đặt thành công SVN | Resources Assigned:
Deliverables: |  | Assumptions: |  | Deliverables: |  | Assumptions:
Project Name: |  |  |  | Project Name:
Work Package ID: | 1.1 |  |  | Work Package ID: | 2.1
Work Package Name: | Read and edit |  |  | Work Package Name: | What?
Work Package Description: | Đọc từng chương, viết lại theo từng mục |  |  | Work Package Description: | SVN là gì? Tìm hiểu sợ lược về SVN
Assigned To: | Son Doan, Duc Tran, Thao Pham, Nhut Huynh | Group/Dept: | 15HTH02 | Assigned To: | Duc Tran | Group/Dept: | 15HTH02
Date Assigned: | 2016-09-20 | Date Due: | 2016-09-30 | Date Assigned: |  | Date Due:
Estimated Cost: | N/a | Account Code: |  | Estimated Cost: | N/a | Account Code:
Acceptance Criteria: | Có chỉnh sửa file text | Resources Assigned: | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7 | Acceptance Criteria: |  | Resources Assigned:
Deliverables: |  | Assumptions: |  | Deliverables: |  | Assumptions:
Project Name: |  |  |  | Project Name:
Work Package ID: | 1.2 |  |  | Work Package ID: | 2.2
Work Package Name: | Check error |  |  | Work Package Name: | Do what?
Work Package Description: | Đọc từng chương đã được sửa lại và kiểm tra lỗi chính tả, ngữ pháp, câu cú. |  |  | Work Package Description: | Tìm hiểu về công dụng và tính ứng dụng cùa SVN
Assigned To: | Son Doan, Duc Tran, Thao Pham, Nhut Huynh | Group/Dept: | 15HTH02 | Assigned To: | Duc Tran | Group/Dept: | 15HTH02
Date Assigned: | 2016-09-21 17:24 | Date Due: | 2016-09-24 17:24 | Date Assigned: |  | Date Due:
Estimated Cost: | N/a | Account Code: |  | Estimated Cost: | N/a | Account Code:
Acceptance Criteria: | Rename file == "xxx(Final).txt" | Resources Assigned: | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7 | Acceptance Criteria: |  | Resources Assigned:
Deliverables: |  | Assumptions: |  | Deliverables: |  | Assumptions:
Project Name: |  |  |  | Project Name:
Work Package ID: | 1.3 |  |  | Work Package ID: | 2.3
Work Package Name: | Complete |  |  | Work Package Name: | Compare
Work Package Description: | Đọc từng chương đã được sửa lại, ghép và hoàn thành file .docx |  |  | Work Package Description: | So sánh với các công cụ khác (Git, CVS)
Assigned To: | Nam le | Group/Dept: | 15HTH02 | Assigned To: | Duc Tran | Group/Dept: | 15HTH02
Date Assigned: | 2016-09-24 17:24 | Date Due: | 2016-09-27 17:24 | Date Assigned: |  | Date Due:
Estimated Cost: | N/a | Account Code: |  | Estimated Cost: | N/a | Account Code:
Acceptance Criteria: | 1 file .docx hoàn chỉnh | Resources Assigned: | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7 | Acceptance Criteria: |  | Resources Assigned:
Deliverables: |  | Assumptions: |  | Deliverables: |  | Assumptions:
Project Name:
|  |  |  | Work Package ID: | 2.4
|  |  |  | Work Package Name: | Setup
|  |  |  | Work Package Description: | Hướng dẫn cài đặt chương trình cho người dùng
|  |  |  | Assigned To: | Duc Tran | Group/Dept: | 15HTH02
|  |  |  | Date Assigned: |  | Date Due:
|  |  |  | Estimated Cost: | N/a | Account Code:
|  |  |  | Acceptance Criteria: | Tạo tài khoản thành cộng | Resources Assigned:
|  |  |  | Deliverables: |  | Assumptions: | Trong điều kiện lý tưởng
Project Name:
|  |  |  | Work Package ID: | 2.5
|  |  |  | Work Package Name: | Function
|  |  |  | Work Package Description: | Tìm hiểu các chức năng ví dụ như: Commit, Update, Merge, Revert của SVN
|  |  |  | Assigned To: | Duc Tran | Group/Dept: | 15HTH02
|  |  |  | Date Assigned: |  | Date Due:
|  |  |  | Estimated Cost: | N/a | Account Code:
|  |  |  | Acceptance Criteria: | Tạo tài khoản thành cộng | Resources Assigned:
|  |  |  | Deliverables: |  | Assumptions: | Trong điều kiện lý tưởng
Formulas:
PMBOK2012-5rd Edition = [Translate Google]+3

## Emai-SMART
From: | leqnam@live.com
To: | sondoan1204@gmail.com; minhducit1993@gmail.com; pnnthao230194@gmail.com; nhuthm080280@gmail.com
CC:
BCC:
Subject: | Bảng phân công công việc cho dự án Quản lý dự án phần mềm
Content:
Chào mọi người,
Để phục vụ cho môn học Quản lý dự án phần mềm đạt kết quả tốt nhất, sau đây là bảng mô tả và phân chia công việc cho môn học này.
Nếu có thắc mắc gì, hãy liên lạc với tôi để được giải đáp.
Đề tài: Tìm hiểu và cách sử dụng SVN trong quản lý source code, dịch thuật tài liệu Chương 6 trong quyển PMBOK2012-5rd_Edition
của công ty Project Management Institute Inc,
| Công việc | Thực hiện | Thời gian dự kiến(h) | Note
| Phân chia công việc, tổng hợp, giám sát tiến trình | Nam Le | 4
| Dịch chương 6 bằng google translate, chia ra thành 7 file txt upload len host | Nam Le; Son Doan | 40
| Đọc từng chương, viết lại theo từng mục | Son Doan, Duc Tran, Thao Pham, Nhut Huynh | 16
| SVN là gì? Tìm hiểu sợ lược về SVN | Nam Le | 8
| Đọc từng chương đã được sửa lại và kiểm tra lỗi chính tả, ngữ pháp, câu cú. | Son Doan, Duc Tran, Thao Pham, Nhut Huynh | 8
| Tìm hiểu về công dụng và tính ứng dụng cùa SVN | Duc Tran | 8
| Đọc từng chương đã được sửa lại, ghép và hoàn thành file .docx | Nam Le | 16
| So sánh với các công cụ khác (Git, CVS) | Duc Tran | 8
| Hướng dẫn cài đặt chương trình cho người dùng | Duc Tran | 8
| Tìm hiểu các chức năng ví dụ như: Commit, Update, Merge, Revert của SVN | Duc Tran | 16
|  | Total: | 132 | hours (8hrs/day)
Thân chào,
Lê Quốc Nam
Trưởng dự án, nhóm 6, 15HTH02, HUTECH

## AON
Bước | Công việc | Công việc trước | Ước lượng | ES | EF | LS | LF
1 | A |  | 1 | 1 | 1 |  |  | 1
2 | B | 1 | 3 | 2 | 4 |  |  | 1
3 | C | 1 | 2 | 2 | 3 |  |  | 2
4 | D | 2 | 5 | 2 | 6 |  |  | 3
5 | E | 3 | 2 |  | 1 |  |  | 4
6 | F | 4 | 3 |  | 2
7 | G |  |  |  | -1
8 | H |  |  |  | -1
9 | I |  |  |  | -1
10 | J |  |  |  | -1